## Sheet1
Task | Assigned to | Start Date | Duration | End Date | Stage
Testing Plan | Conor | 2019-01-29 | 1 | 2019-01-30 | 2
QA Plan | Ibraheem | 2019-01-29 | 2 | 2019-01-31 | 2
Project Management Plan | Alice | 2019-01-29 | 1 | 2019-01-30 | 2
Review Plan | Isaiah | 2019-01-29 | 3 | 2019-02-01 | 2
Version Control Plan | Kieran | 2019-01-29 | 2 | 2019-01-31 | 2
Gantt Chart Template | Alice | 2019-01-30 | 2 | 2019-02-01 | 2
Original Class Diagram | Ibraheem and Isaiah | 2019-02-01 | 7 | 2019-02-08 | 3
Basic Login & Logout Implementation | Alice and Kieran | 2019-02-05 | 1 | 2019-02-06 | 3
Access Level Login | Alice and Kieran | 2019-02-05 | 2 | 2019-02-07 | 3
Creating Personal Records | Alice and Kieran | 2019-02-09 | 2 | 2019-02-11 | 3
Changing Access Levels | Alice and Kieran | 2019-02-09 | 3 | 2019-02-12 | 3
Logging Authorisation attempts | Alice and Kieran | 2019-02-13 | 3 | 2019-02-16 | 3
Test Classes | Conor | 2019-02-11 | 6 | 2019-02-17 | 3
Updated Class Diagram | Conor, Kieran, Alice | 2019-02-26 | 2 | 2019-02-28 | 4
Updated Creating Personal Records | Alice and Kieran | 2019-02-22 | 1 | 2019-02-23 | 4
Creating Review Records | Alice and Kieran | 2019-02-28 | 1 | 2019-03-01 | 4
Updated Logout Implementation | Alice and Kieran | 2019-02-22 | 1 | 2019-02-23 | 4
Updated Changing Basic Access Levels | Alice and Kieran | 2019-02-28 | 1 | 2019-03-01 | 4
Updated Login Implemetation | Conor | 2019-02-28 | 2 | 2019-03-02 | 4
Storing Logging Authorisation Attempts | Ibraheem and Isaiah | 2019-02-19 | 7 | 2019-02-26 | 4
Creating Record Files | Ibraheem and Isaiah | 2019-02-20 | 2 | 2019-02-22 | 4